## Flow Diagram
WCC - Targeted Testing Programme Plan | x
SETUP Flow Diagram
The following is a high level flow diagram outlining the areas of setup you will need to complete for your LFT site
Note this is not a comprehensive list - this simply gives a general idea of the areas of work and a suggestion of the basic order you should look to do them in
Note the next tab provides a more complete checklist of all the individual actions you need to consider to setup of your LFT site
The Support tab at the end contains all the released training and guidance, as well as a selection of resources and tools
DEVELOPMENT PHASES
1. Confirm test kit / PPE delivery received ok. Contact DfE with any issues
2. Store Test kits / PPE delivery in suitable storage and record stock levels (remembering temperature requirements)
3. Begin registration process by registering your Team Leader and setting onto the test recording site (can take 48 hrs to be approved)
START
1. Identify Testing site location(s) and requirements
2. Confirm all required equipment / materials and begin procurement process
3. Identify staffing requirements and begin recruitment process
4. Identify required signage / infomation needs
5. Identify all key process requirements (consent, registration, recording etc)
6. Identify all required QA / performance monitoring documentation for use in running testing site
7. Plan out anticipated testing process / schedule
1. Put together testing site. Chase any outstanding equipment / material needs
2. Complete recruitment
3. Register all staff onto test recording site
4. Develop training materials as required for staff / students
5. Develop all key process requirements (consent, registration, recording etc) and create tools / templates / letters as needed
6. Develop any required QA / performance monitoring documentation for daily use in testing site
7. Send out communications to all stakeholders advising of planned testing schedule and processes
1. Review Testing Site and complete Risk Assessments
2. Confirm receipt of all required equipment and materials
3. Staff to complete web / classroom training
4. Complete practical training for staff by having them perform tests on each other
5. Sign off all staff and test site
6. Review all process and documentation to ensure everything is complete and available
7. Address any concerns / feedback from stakeholders
1. Commence LFD testing
2. Record all registration, consent and test details
3. Submit results to test recording site and any other submission requirements
4. Monitor staff performance via checklists / QA documentation
5. Monitor consumable stock levels and complete restocking as required
6. Continuously review and get feedback on process to amend, improve, update documentation as required
END
FIRST PRIORITIES
DESIGN
DEVELOPMENT
IMPLEMENTATION
LAUNCH

## SETUP Checklist
WCC - Targeted Testing Programme Plan
SETUP Checklist
The following is a checklist of all areas and tasks that will need to be covered in order to establish your setting to support LFT |  |  |  |  | Acronyms: LFD = Lateral Flow Device LFT = Lateral Flow Testing PII = Personally Identifiable Information QA = Quality Assurance
Columns have been added (F & G) to record your progress against each item and for comments should you wish to use this form to monitor and record progress
Further information on the below items is provided within the support documentation that has been created - links to these are found within the SUPPORT tab
Note that Standard DfE guidance especially around SOCIAL DISTANCING must be adhered to in all of the below
Initial Actions - NOTE these steps must be actioned AS SOON as delivery arrives
Section | No. | Task | Notes / Info | Current Status | Setting Notes
Initial Delivery |  | Review initial delivery to confirm all stock delivered correctly and no items missing / incorrect / damaged. Notify DfE with any issues | See link on CONTACT & SUPPORT tab for contacting DfE
|  | Move all stock into suitable storage ensuring ambient temperature for all LFD storage is kept between 2 - 30 degrees at all times | See 'Site Requirements' steps below for more details on storage requirements
|  | Log consumable stock inventory levels onto spreadsheet for future monitoring | See 'Processes' steps below for more details on stock management
Registration |  | Appoint Team Leader and register them onto test recording site - note it can take up to 48 hrs to be approved | Needs to be done IN ADVANCE of commencement of testing Link for Team Leader to register is available on CONTACT & SUPPORT tab
Site Requirements
Section | No. | Task | Notes / Info | Current Status | Setting Notes
Space & layout |  | Setup main testing room in line with guidance and social distancing | For unregistered Independent / Alternative Providers there may be some capacity to accommodate testing within a community test centre if you have not received any testing kits and/or have no space to set up your own test centre. Consider additional spacing requirements to support students who may need support staff, be in wheelchairs or have other mobility / support needs Consider needs at both initial (mass) testing stage and later (serial) testing stage See Government Testing handbook for proposed layouts. Note also that from the testing experience at Community sites: - Test swabbing and processing activities can be completed at the same desks - A single recording desk can handle test results from up to 10 swabbing / processing desks
|  | Setup Recovery room for students in line with social distancing | > This room is specifically for students who have bad reactions to the swabbing process. From feedback we understand the pilot sites sent students generally to tutor rooms following testing so the bubble did not mix with the rest of the school while they were waiting for their results. > For serial testing it may be possible to identify an additional room for students to wait in while awaiting results before releasing them in to the wider school
|  | Setup Staff Room for all staff involved in testing in line with social distancing | > The staff room should be next to the testing site so staff do not have to walk through the school to get to it. > If a school are employing external staff it would be better to not use current staff rooms used by normal teaching staff. > Wherever possible a seperate staff room should be set up
Identify suitable isolation room to bring positive cases to whilst awaiting collection
|  | Identify any other room requirments you might have | Any need for this is dependant on how you wish to run your testing
|  | Check access is suitable across whole testing site, including for students in wheelchairs or with other access requirements | This is of special note for special schools / alternative provisions
Ensure adequate access to toilets for all testing staff and students
Ensure suitable parking in place for transport to deliver students safely
Ensure testing site has suitable and unobstructed fire exits with clear signage
Identify suitable evacuation and assembly points for testing facility
Ensure adequate space available for students to queue both whilst awaiting registration and testing
Identify suitable space to move students to who are having issues or are not willing to proceed with testing
Identify one-way flow system for students to move through the testing facility
Put up appropriate signage to identify one-way route through testing site
Ensure posters and banners are displayed to outline & support process
|  | Additional helpdesk available out front for queries / issues? | Setting to determine whether they deem this necessary or not
Storage |  | If testing facility is not going to be left up permanently, identify suitable storage facility for all equipment and infrastructure including signage, partitions etc
|  | Identify suitable storage for all consumables including PPE, cleaning materials and all testing materials | Remember that test kits need to be kept at 2-30 degrees while stored (15-30 during use) to ensure that the reagent does not become ineffective.
Identify suitable location for secure storage of clinical waste prior to collection
Environment |  | Ensure flooring is suitable (i.e. hard flooring that can be wiped / moped down easily)
Ensure furniture is suitable and can be easily wiped down
Ensure good airflow is maintained through the testing facility
|  | Check storage temperature for all used and unused LFD devices is maintained between 2 - 30 degrees at all times whilst in storage | Remember while in use the LFD kits should be kept between 15 - 30 degrees
|  | Ensure temperature of testing rooms is maintained between 15-30 degrees while in operation | Needed both for proper operation of LFD kits and as a legal requirement for admin staff's working environment
Ensure adequate lighting
Have gritting available for outdoor locations (e.g. parking and queueing and registration)
Materials
Section | No. | Task | Notes / Info | Current Status | Setting Notes
Site |  | Suitable tables & chairs for desks | As a minimum testing site will require a minimum of 3 main areas / desk types: - registration - swabbing & processing - recording & reporting This is the setup used in the Community Test Centres. Dfe guidance suggests splitting the swabbing and processing activites onto seperate desks. Therefore, in essense there are two main options: Option 1: Use DfE gudiance using separate swabbing / processing desks Option 2: Use the same desk to perform both functions (Swabbing and Processing) There is guidance in the training materials on desk layouts
Booths / screens as required around desks
Barriers for registration queues if required
Appropriate safety devices (e.g. fire extinguishers, defibrillators etc)
|  | Waste bins | > Note there are multiple types of waste that will be collected. Some bins will need to be specifically at certain desks (see below) > See training guidance in CONTACT & SUPPORT tab for more information on the different types of waste collection you will need to do
Fan / space heaters if required for ambient temperatures at desks
|  | Suitable information materials including: - One-way arrows - Information posters - Pull up banners | See the SUPPLIER LIST tab
Registration Desk |  | Equipment: - Laptop / computer or other device for recording student attendance, consent & registration | > See DESK LAYOUT tab for a quick guide on desk contents (if you are setting up the desks in accordance with the training guidance - this might be different if you decide to set the desks differently) > There may be some additional recommended items in the below list above what is in the training - this is based on feedback from the Community testing centres > See training materials in CONTACT & SUPPORT tab for full details on required desk equipment
Consumables: - Registration forms & barcodes - Disinfectant spray - Paper towels - Hand sanitizer
Swabbing Desk |  | Equipment: - Sick bucket - Clinical Waste disposal bin - Mirror - Sign to indicate station needs cleaning
Consumables: - Disinfectant spray / wipes - Swabs - Tissues - Hand sanitizer - Disinfectant spray - Paper towels
Processing Desk |  | Equipment: - Clinical waste disposal bin - Test Tube rack - Vials - Tray to transfer tests - Pens / pencils / markers | As noted at the start of this section you might chose to incorporate the Swabbing and Processing functions within the same desk. The two options are as follows: Option 1: Use DfE gudiance using separate swabbing / processing desks Option 2: Use the same desk to perform both functions (swabbing and Processing)
Consumables: - LFD Devices - Gloves - Disinfectant spray - Paper towels
Recording Desk |  | Equipment: - Normal waste disposal bin - Timing clock(s) - Laptop for recording results | Note the guidance advises the timing devices to go on the processing desks. In practice in community sites the tests have been passed straight over to the recording desks who run the timers and record the results at the end of the time
Consumables: - Disinfectant spray - Paper towels
Staff |  | Access to full PPE including: - Aprons - Gloves - Masks / visors | Please see the SUPPLIER LIST tab
Hi Viz jackets as required
Badges / identification
Other |  | Tea/coffee/milk/sugar/disposable cups etc for site welfare
Catering if required for testing site staff
Additional clinical waste and ordinary bags (for double bagging if required)
Cleaning products
Stock of umbrellas for people who may be queueing outdoor in rain (plastic handles that can be wiped down)
Miscellaneous as required (including mobile phones, scanning devices, whiteboards, printers, tools as required)
Staffing
Section | No. | Task | Notes / Info | Current Status | Setting Notes
Recruitment |  | Confirm staffing and funding requirements | Calculation tool is available on CONTACT & SUPPORT Tab - 'Workforce Planning Tool' Redeployment of existing staff: If employees agree to undertake a different role and/or working pattern they should continue to be paid at their normal contracted rate. Where they are temporarily undertaking roles that are paid at a higher rate than their usual contracted rate they should receive the higher rate of pay for the duration of the assignment/redeployment. Arrangements should be made to pay the higher rate as soon as practically possible Some settings have noted that having an Administrator role in addition to the Team Leader has proved helpful in keeping the test site moving and avoiding delays.
|  | Identify and complete additional staffing recruitment as required | ALL STAFF ARE REQUIRED TO BE DBS CHECKED Agency Staff: Frameworks are available to access agency staff, further guidance will be issued by DfE. Warwickshire County Council has an existing contract with Pertemps. Pertemps are an approved Public Sector supplier of staff via a number of frameworks and have developed a Taskforce delivery model & Management Team for the provision of screened and vetted agency staff to support Covid related initiatives. See contact details in CONTACT & SUPPORT tab
|  | Complete Risk Assessments for any vulnerable members of staff to confirm they can participate in the testing | Recommended this is done early in the process to limit any exposure of these staff to higher risk activity
|  | Complete 'Reinstatement Risk Assessments' for any NEW members | This document is available within the CONTACT & SUPPORT tab
|  | Consider any additional staffing requirement to support students with mobility or other SEN | Further guidance will be issued by DfE
Staff Registration |  | Registration of Test Centre: > Team Leader to Register first (can take up to 48 hrs) > Test operatives to be registered and approved by Team Leader | Needs to be done IN ADVANCE of commencement of testing Link for Team Leader to register is available on CONTACT & SUPPORT tab
Staff Training |  | Review of DfE guidance handbook(s)
Completion of DfE web training
Completion of required site training (facilities, fire escapes etc)
Safeguarding training
Complete initial group practical training including all staff to have swab test
|  | Sign off all training | All training must be completed and staff must pass assessments and be signed off ahead of commencing testing
Student Training |  | Create videos / presentations and other training materials to explain the testing process to your students | To help students feel familiar and relaxed about the process, training materials should try to be as exact to your specific setup as possible. This may be especially important to Special Schools, Alternative Provisions and any SEN students.
Consider setting up a 'walkthrough' of the testing process for students to observe (possibly involving a member of staff getting tested)
Processes - NOTE a lot of these are outlined in the training and guidance already provided (see links in the CONTACT & SUPPORT tab)
Section | No. | Task | Notes / Info | Current Status | Setting Notes
General |  | Engage with military logistical / planning support as required
|  | Update / create risk assessments to cover testing site and review existing COVID risk assessments | > Note that this does not mean a setting needs to complete a whole new risk assessment. A setting's current COVID risk assessment can be updated to include consideration of the Testing site. > Sample risk assessment is available on Support tab - 'Risk Assessment Template' if a setting wishes to create a new assessment for this activity > Ensure you also review your existing COVID risk assessment to see if any other controls / procedures need updating in light of implementing LFT
|  | Initial registration of Test Centre | Needs to be done IN ADVANCE of commencement of testing
|  | Overall Customer journey for student | Slides provided by DfE. See training documents in CONTACT & SUPPORT tab
|  | Additional Support requirements for EHCP & SEN students | Additional guidance is due to be released on how to support SEN students who are struggling to self-administer a test
|  | Staff process map | Slides provided by DfE. See training documents in CONTACT & SUPPORT tab
|  | Staff roles and responsibilities | Slides provided by DfE. See training documents in CONTACT & SUPPORT tab
|  | Create anticipated school testing schedule | It is recommended to try to perform testing in the morning as much as possible. This allows the maximum amount of time before the end of the day to do follow-up actions such as chasing up void results, following up positive cases, submiting test results and so on
|  | Create staff rota | It is recommended to try to keep a largely consistent team as far as possible at the start of the process to allow an experienced group to develop quickly
|  | Ongoing testing policy to include: - Initial mass testing of whole school (2 tests in 5 days for all staff students) - Ongoing weekly staff testing - Serial testing for contacts of positive cases - Temporary / cover and other part-time staff - Students on partial timetables or attending multiple settings - New starters during school year - Students on school roll but educated elsewhere | > Staff / students should continue being tested even if they have been vaccinated > Some additional information regarding testing students who attend an Alternative Provision can be found on the CONTACT & SUPPORT tab in 'Alternative Provision LFT advice' > Visitors to site do not need testing
|  | Processes for children who have not consented to testing | > All Consent decisions should be recorded for future reference (and to prevent a student who does not consent being asked multiple times) > Students who refuse testing can continue to attend school providing they do not have any COVID symptoms
Agreed scripts for student-facing staff members
Registration |  | Consent process: - Reading of privacy notice and questions and confirming understanding - Confirming Student consent and consent forms - Recording consent - Any alternative / enhanced consent requirements for EHCP / SEN students | > Consent must be given in written / electronic format - verbal consent is not acceptable > Consent giver must understand that personal data is processed as a result of this test, privacy notice to be read and questions asked prior to giving consent > In most cases 16+ students can give consent themselves with exceptions for looked after children > Students under 16 will need consent from parent / guardian > Alternative Provision and Special School settings will need to give additional consideration to suitable consent processes > 16-25 yr. SEN children do not need parental consent where they can make a decision for themselves. This is to be determined by the setting and the setting may wish to consider a medical capability assessment. A record of how consent has been given must be recorded and kept > It is recommended to record where consent is refused to avoid further requests being made
|  | Registration process: - Confirming Student consent and consent forms - Completing student registration - Registering test kit against student - Allocation to student of unique barcode for each day's test | Students can be registered up to a maximum of 24hrs before the test is taken
Queue management
Support for students missing ID's or with other issues
Testing |  | Testing process: - Limits on how staff can support student to complete test - Completing swabbing - Process swab with test kit | > Staff are not allowed to provide advice on the swabbing process other than reiterating the official process guidance from the DfE verbatim > An Info poster on how to self-administer a Test is provided in the CONTACT & SUPPORT tab and is recommended to be clearly visible to support the student > The DfE helpline can be used to provide further support
Managing spillage of bodily substances
|  | Managing students unwilling to proceed with test once in testing area | Need to be able to record decision and remove student from testing area whilst maintaining social distancing
Wipe-downs by testing staff of their side of testing area following completion of each test
Wipe-downs by cleaning staff of student side of testing area following completion of each test
Recording & Reporting |  | Recording of student consent checks into internal system
|  | Recording of all test results (student and staff) into internal system | Results (minus personal details) should be kept by the school as results will they not be accessible from test and trace data site
|  | Submission of test results into Test & Trace system | > Positive results must be recorded within 24hrs of test > Negative / void results can be recorded up to 7 days after test
Logging of: - Safety concerns - Safety issues - Serious incidents
Consumable stock inventory levels
Completion of additional DfE and PH reporting requirements
Follow-up |  | Calling back student in event of void test
|  | Follow-up testing and isolation protocols for positive student | > Students will need to be moved to an isolation area away from other students / staff prior to collection by parents. They will need to remain there until collected by parents or another suitable transport arrangement is reached > Students should be advised to take a confirmatory PCR test and isolate if required based on results.
Identifying and enhanced testing for contacts of positive student
|  | Record retention policy | > All records should be kept for a minimum of 14 days from creation > After 30 days all PII (personally identifiable information) must be removed from records. You can keep the data on consent agreements and test results but it MUST have all information linking back to individual students removed
PH Waste Disposal (Regulated) |  | Disposal of Clinical Waste (including bins, bags, containers) | Check information in CONTACT & SUPPORT tab for more information
Disposal of PPE (Category 2 - Clinical waste)
Disposal of swabs etc. (Clinical waste)
Disposal of bodily waste (e.g. vomit)
Site Management |  | Monitoring consumable stock levels
Stock reordering & receipt
Stock storage
Daily QA monitoring
Monitor Staff wellbeing and working hours
Start-up processes at beginning of daily testing
Cleaning down processes at end of daily testing
Comms & Engagement - NOTE Templates and guides are provided in the CONTACT & SUPPORT tab for the below
Section | No. | Task | Notes / Info | Current Status | Setting Notes
Communications |  | Send suitable communication of testing plans, considerations and student impacts to parents | Fully consider student impact - what times should they turn, what do they need to bring, any additional clothing requirements if queueing outside etc
Send suitable communication of testing plans, considerations and impacts to staff, governors and other stakeholders
Update and circulate timetables as required
Circulate information regarding the testing process to all stakeholders
On Site |  | Ensure suitable signage in place directing students on site including labels for desks and one-way arrows on floors
Put information posters and pull up banners around site

## DAILY Checklist
WCC - Targeted Testing Programme Plan
DAILY Checklist
The following is a checklist to identify all the recommended checks and processes you should be carrying out daily to ensure successful ongoing management of your testing facility
Columns have been added (F & G) to record your progress against each items and for comments should you wish to use this form to monitor and record your progress
Note that Standard DfE guidance especially around SOCIAL DISTANCING must be adhered to in all of the below
Before Testing
Section | No. | Task | Notes / Info | Current Status | Setting Notes
Site |  | Open up and set up testing site room - including desks, booths, screen etc
Setup / check student recovery room in line with social distancing
Setup / check student isolation room in line with social distancing
Setup / check staff room in line with social distancing
Setup / check any other rooms / spaces you are using as part of your test site
Check toilet facilities
Check fire exits and assembly points are clear and unobstructed
Put out any barriers required for queueing area
Put out posters and banners and any other signage
Environment |  | Check good airflow on site
Check temperature in storage areas for all LFD tests (used and unused) between 2 - 30 degrees
Check ambient temperature and put out heaters as required to bring working areas up to 15-30 degrees
Check lighting still adequate
Check outdoor areas and routes into testing are suitable (e.g. to see if gritting needed)
Staffing |  | Complete and save register for staff in attendance
Confirm suitable levels and expertise of staff on site to run testing centre. Make alternative provisions as required if not
Carry out any pre-shift briefing as required with staff
Complete LFD test and record results for all test site staff every day
Any staff with positive test results to be sent home and follow-up actions to be followed (clean down area, staff member to take PCR test and isolate as required following PCR test)
Equipment |  | Put out required equipment / consumables at all desks
Put out / make available suitable equipment and consumables for testing site
Put out any other requirements (tea / coffee facilities, umbrellas for outside, required devices etc)
Recording |  | Check through all recording and reporting logs. Update to add in sections for today's testing as required
During Testing
Section | No. | Task | Notes | Current Status | Setting Notes
Environment |  | Monitor airflow on site
Monitor ambient temperature in storage areas for used and unused LFD tests to ensure stays between 2 - 30 degrees
Monitor ambient temperature HOURLY for working areas between 15-30 degrees
Monitor lighting
Equipment |  | Monitor equipment / consumable stocks at desks. Restock as required throughout day
Staffing |  | Ensure staff have appropriate breaks
Rotate staff around roles
Monitor staff wellbeing
Processes |  | Monitor staff performance and all core processes around testing, recording and reporting | See Checklists in the CONTACT & SUPPORT tab: > 'Sample Quality Checklist' > 'Competency checklist for key roles'
Monitor queue levels and overall throughput and efficiency
Monitor storage of all completed tests into storage facility
Monitor recording of all test results and other reporting requirements are carried out correctly
Monitor positive / void cases actioned and follow-up actions carried out promptly and correctly
Follow up any complaints / process issues
After Testing
Section | No. | Task | Notes | Current Status | Setting Notes
Site |  | Return all equipment and unused consumables to storage
Collect signage / barriers and return to store
Ensure all completed tests added to storage and check ambient temperature in storage areas for used and unused LFD tests is still between 2 - 30 degrees
Empty and store / dispose of all waste materials appropriately. Ensure different types of waste are handled in accordance with their type (e.g. clinical waste)
Conduct thorough clean down of all testing and support areas
Ensure no belongings left behind by staff / students
Switch off equipment / lighting and secure site as required
Equipment |  | Review equipment for any damaged / non-functioning items and replace or complete stock reordering process as required
Review consumable stock levels and complete stock reordering process as required
Reporting |  | Review all reporting and logging completed accurately
Ensure any void cases have been followed up
Ensure all positive cases have been followed up and suitable next steps followed and contacts identified
Ensure all reporting requirements sent off as required to DfE, PH and any other required bodies
Staffing |  | Gather staff feedback
Ensure suitable staffing levels / expertise are booked in for running the test facility the next day
Process |  | Ensure all complaints / process issues have been followed up
Review any other lessons learned / suggested improvements received

## SUPPLIER List
WCC - Targeted Testing Programme Plan
KIT & SUPPLIER list
The following is a list of some of the key items you will need for your LFT site (list may not be 100% complete for your specific site requirements)
Below this is a Suppliers and website / contact information list for various items you may require to order (this list may be added to / amended over time)
1 - Required Kit
PROVIDED BY NHS TRACK & TRACE | PROVIDED BY SETTING
> Lateral Flow Test kits | > Test site (e.g. school hall, classroom) | > General waste bin
> Barcodes | > Tables | > Clocks / timer
> Waste disposal bags | > Chairs | > Mirrors
> PPE: disposable gloves | > Hand sanitiser | > Trays to transfer tests to the processing table
> PPE: disposable plastic aprons | > Disinfectant wipes; tissues | > Tube racks or equivalent (can be microarray test tube racks)
> PPE: Type 11R surgical masks | > Mop & bucket | > Tape and / or plastic sheets to separate testing bays
> PPE: eye protection (goggles / visors) | > Signage that can be cleaned and laminated instructions on swabbing and processing for each bay | > First aid supplies
> Bowls | > Computer(s) for test registration upload | > Stationary supplies incl: markers, pens, printers
> If you want to automatically scan barcodes you may want to purchase a barcode scanner or through browser based application
2 - Supplier Contact List
Supplies | Supplier 1 | webpage
Equipment
PPE | PROVIDED by DfE if missing items go to DfE website and locate the form or use the help line 0800 046 8687 | 0800 046 8687
Timers x 2 | Amazon | https://www.amazon.co.uk/Salter-Minute-Mechanical-Kitchen-Timer/dp/B01AFNR658/ref=sr_1_8?dchild=1&keywords=clocks+and+timers&qid=1609862432&sr=8-8
Barriers/ Screens | Test consumables and ATS/Test station booths are to be sourced by DfE but we pay for them and recover the costs | n/a
Fan/ Space heaters | ESPO | https://www.espocatalogue.org/WebConnectEPO/MainServlet?storeId=webconnect&catalogId=webconnect&langId=en_GB&action=ProductDisplay&screenlabel=index&productId=44384
hand/table Mirrors | Argos | https://www.argos.co.uk/product/4085997?clickSR=slp:term:mirror:10:119:1
Bins - general waste | ESPO | https://www.espocatalogue.org/WebConnectEPO/MainServlet?storeId=webconnect&catalogId=webconnect&langId=en_GB&action=ProductDisplay&screenlabel=index&productId=46301
clinical bin liners | PROVIDED by DfE if missing items go to DfE website and locate the form or use the help line 0800 046 8687 | 0800 046 8687
clinical waste disposal | Check with your normal supplier if they will take Health Care waste from testing in yellow/ clear bags and those in tiger bags? Dispose via your normal route | www.biffa.co.uk
Tape or plastic sheets to separate testing bays | ESPO | https://www.espocatalogue.org/WebConnectEPO/MainServlet?storeId=webconnect&catalogId=webconnect&langId=en_GB&action=ProductDisplay&screenlabel=index&productId=43766
Tube racks or equivalent | Amazon | https://www.amazon.co.uk/s?k=test+tube+racks&crid=35RLXVATGJXS6&sprefix=test+Tube+racks%2Caps%2C190&ref=nb_sb_ss_ts-a-p_1_15
First aid kit | ESPO | https://www.espocatalogue.org/WebConnectEPO/MainServlet?storeId=webconnect&catalogId=webconnect&langId=en_GB&action=ProductDisplay&screenlabel=index&productId=44019
Consumables
Hand Sanitiser | Express Cleaning Supplies | www.ExpressCleaningSupplies.co.uk
Pens/ Pencils/ Permanent Markers | ESPO | www.espo.org
Disinfectant spray | Express Cleaning Supplies | www.ExpressCleaningSupplies.co.uk
Tissues & wipes | ESPO | www.espo.org
Paper Towels | ESPO | www.espo.org
Testing kits
Swabs | PROVIDED by DfE if missing items go to DfE website and locate the form or use the help line 0800 046 8687 | 0800 046 8687
Cartridges
Extraction tubes
Extraction solution
Barcodes
User manual / guidance
Test receipt(s)
QR codes (given by receptionist)
Signage
Arrows | Indoor ones came from WCC Business Support (print services) Outdoor e.g. banners are provided by Events Specialist | WCC Business Support (print services)
Testing posters
Social distance posters
Pull up banners |  | EventSpecialistltd.com
Information tests

## Desk Layout
WCC - Targeted Testing Programme Plan
Desk layouts
The below is a screengrab of the infographic provided in the training which identifies what equipment is needed at each of the desks in the test site
More information on this is available in the training and guidance on the CONTACT & SUPPORT tab
It should be noted that in the Community test centres it was found that the Swabbing and Processing desks can be combined into the same desk
(whether you follow this layout or the one outlined within the training is up to yourself)

## Contact & Support
WCC - Targeted Testing Programme Plan
Contact details and supporting materials
Below are the contact details and key support resources that are available. Note these resources may be added to / updated over time
Many of these links go into the Google drive site where the latest version of these resources will be kept (and new documents will be added)
NOTE - over time some of the google links may stop working if the folder structure changes. In that instance just click one of the 'Google - Main' link belows and follow the new folder strucutre in the drive
It is recommended you start with the below identified training materials in the first section
1 - Contact Details
For raising questions, concerns & issues |  |  | For reporting any issues with delivery of test kits
DfE Coronavirus helpline: | 0800 046 8687 (Available Mon-Fri 8am-6pm, Sat-Sun 10am-6pm) |  | GOV.UK: | https://form.education.gov.uk/service/rapid-testing-contact
RapidTesting.SCHOOLS@education.gov.uk
For any media queries or if approached by a member of the media |  |  | For Registering a Team Leader
DHSC Press Office: | 020 7210 4850 |  | GOV.UK: | https://www.education.gov.uk/register-testsite-team-leader
https://www.gov.uk/government/organisations/department-of-health-and-social-care/about/media-enquiries
For requesting Agency staff from Pertemps
Pertemps: | 0800 011 2783
hello@pertemps.co.uk
2 - Support Documents
Resource Type | Resource Description | Format | Description |  | Link / Details
Guides and Training | Delivery Note for Testing Equipment | PDF Doc | IMPORTANT TO READ FIRST - Guidance note on the delivery of testing equipment and PPE to schools and colleges |  | Google - Planning Tools
| NHS How To guide | PDF Doc | A practical step-by-step guide to support all those working in schools and colleges to carry out rapid asymptomatic testing |  | Google - Main
| NHS Digital guidebook | PDF Doc | Guide to support users with the digital services used for the Covid-19 testing |  | Google - Main
| Training Guide for Schools and Colleges | PDF Doc | A short guide to the online training available to support those involved in delivery of rapid testing in schools or colleges. This document also contains a link to the online training course. |  | Google - Training
| Schools and Colleges Overview Handbook (Web) | PDF Doc | Earlier overview handbook of setting up and running testing programme (link off .GOV site) |  | GOV Mass testing page
| NHS Mass Testing in Schools | mp4 Video | High level overview animation to support schools and colleges in setting up the test site |  | Google - Training
| Clinical Standard Operating Procedure (SOP) | PDF Doc | DHSC Guidance on all operational processes and clinical requirements |  | Google - Planning Tools
| NHS Training Webinar 1 | Microsoft Teams Link | Online training - Site Setup, Equipment, Supplies, Logistics and Waste Management |  | Webinar 1
| NHS Training Webinar 2 | Microsoft Teams Link | Online Training - Workforce, training, consent and engagement |  | Webinar 2
| NHS Training Webinar 3 | Microsoft Teams Link | Online Training - Clinical compliance, incidents, outbreaks and recording results |  | Webinar 3
Templates | Risk Assessment Template | PDF Doc | Risk Assessment template for running of LFT site |  | Google - Templates
| Model Privacy Notice | Word Doc | A model privacy notice for schools and colleges to update and share with parents or carers/guardians |  | Google - Templates
| Consent Form | Word Doc | Editable consent form for schools and colleges to share with parents or carers/guardians |  | Google - Templates
| Letter template | Word Doc | Editable overview letter for parents / guardians (link off .GOV site) |  | GOV Mass testing page
| Various Letter templates | Word Doc | Various letter templates for staff / parents / stakeholders and waste providers |  | Google - Letter Templates
| Reinstatement Employee Risk Assessment | Embedded Word Doc | Checklist & Risk Assessment for new staff members - i.e. anyone not previously working in the school and considered in previous COVID risk assessments (this copy is an alternative if setting does not have their own version) |  | ß (Click icon twice to open)
Tools | Workforce Planning Tool | Excel Spreadsheet | Editable spreadsheet allowing you to calculate level of funding you will be entitled to |  | Google - Planning Tools
| Sample Quality Checklist | PDF Doc | Overview checklist for Testing quality Lead |  | Google - Templates
| Competency checklist for key roles | PDF Doc | Assessment docs for reviewing competency / performance of key roles within LFT site |  | Google - Templates
Resources | Various Signage | PDF Doc | Various printable signage options for your LFT site |  | Google - LFT Signage
| Info poster on how to self-administer a Test | PDF Doc | Infographic poster on how to self-administer a LFD test |  | GOV Mass testing page
Information | Terms and Conditions Doc from DHSC | PDF Doc | Terms and conditions for carrying out mass testing in schools and colleges, including what support you can expect from government. |  | Google - Main
| Privacy Notice | PDF Doc | Privacy notice for schools and colleges for management of Covid-19 testing. |  | Google - Main
| Job Description Covid Support Testing | Embedded Word Doc | Full job Description of COVID support tester to support recruitment |  | ß (Click icon twice to open)
| Schools and Colleges Delivery Dates & Allocations | Excel Spreadsheet | delivery dates and allocation for schools and colleges |  | Google - Planning Tools
| Live feedback from Poole School | Youtube Video | Feedback from Poole school on their LFT setup |  | Youtube Link
| Data Protection - parent FAQ's | PDF Doc | Parental FAQ's around the Personal Data gathered for LFT testing |  | Google - FAQ's
| Testing - Public FAQ's | PDF Doc | Public FAQ's around the testing process |  | Google - FAQ's
Website | Mass Asymptomatic testing Gov homepage | Webpage | Govt testing homepage (within Education & Childcare during coronavirus pages). Includes additional links (listed separately above) |  | Mass testing GOV page
| Guidance for schools on administering mass testing | Webpage | Info on administering mass testing |  | Administering Testing GOV page
| Education & Childcare during Coronavirus | Webpage | Home GOV page covering all aspects of Coronavirus education / childcare information |  | Coronavirus Education GOV home page